TWG

The Engagement Model

The complete walkthrough · First contact to completed engagement · Every step, every document, every output

Version 1.0   ·   July 2026   ·   Founding team   ·   Confidential

How to Read This Document

This is the operating manual for the TWG engagement model, written so that anyone can run any part of the process without having seen it before. Every step follows the same format: who does it, what happens, which document is used, what the output is, and what triggers the next step. If a step says a document is used, that document exists in the template library. If a handoff happens, it is written down. There are no steps that live in anyone's head.

The model has two entry doors and one engine. Practitioners enter through Journey P. Clients enter through Journey C. The two journeys meet at the Match (Section 3), flow through the Statement of Work (Section 4), Delivery (Section 5), and Money (Section 6), and finish at the Close (Section 7) and what comes after (Section 8). Escalations and exceptions, including late payment and circumvention, are in Section 9. The complete document map is at the end.

⚠  Legal status: the L-series agreements (L02 Practitioner Membership, L03 Client Engagement, L04 Terms and Conditions) are drafted but pending solicitor sign-off. Every step below that uses them is the intended final process. Until sign-off lands, no agreement is executed with any new party. The contracting structure question raised in review (whether TWG is the contracting entity with a subcontract clause, or the SOW runs directly between practitioner and client) is with the solicitor and the answer may adjust steps S3, F1, and F2. This document will be reissued as v1.1 when sign-off lands.

The one-sentence version of the whole model: a verified practitioner and an accountable client are matched against a defined problem, the outcome is agreed and signed before day one, the work is delivered against milestones, the money flows through the network with protection on both sides, and both parties are rated when it ends.

Section 1 · Journey P: The Practitioner

From first conversation to onboarded, working member. Target elapsed time: 20 to 50 days. Owner throughout: the sponsoring founding team member (the person who made or received the first contact).

| P1 | First contact |
| --- | --- |
| Who does it | Any founding team member, or inbound via the website |
| What happens | A conversation happens: outreach from the team, an introduction from an existing member, or an inbound enquiry from the site. The team member gives the standard story: governed network, verified entry, full day rate, published fees, bilateral 360. The membership talking points apply. No documents are shared at this stage beyond what is public on the website. |
| Document used | None (talking points from the Membership Pack) |
| Output | A candidate who wants to see more, or a polite no |
| What triggers next | Candidate expresses interest in seeing the detail |

| P2 | NDA |
| --- | --- |
| Who does it | Sponsoring team member sends; TWG countersigns |
| What happens | The clean execution NDA is sent the same day interest is confirmed. This is the single approved version with no draft markings and the auto-updating date. Nothing else is sent until it returns countersigned. On return, the date field is locked (Ctrl+Shift+F9) and the executed copy is filed in the practitioner's folder. |
| Document used | TWG_Mutual_NDA_v1_Clean |
| Output | Countersigned NDA on file |
| What triggers next | NDA returned signed |

| P3 | Documentation pack |
| --- | --- |
| Who does it | Sponsoring team member |
| What happens | The full practitioner pack goes out the same day the NDA returns: Foundation Document, Founding Practitioner Brief, the Membership Value document (what £350 buys), and the website link. The covering note tells them where to start (Foundation Document first) and invites questions. |
| Document used | Foundation Document v1.2, Founding Practitioner Brief v2, Membership Value doc |
| Output | An informed candidate |
| What triggers next | Candidate confirms they want to apply |

| P4 | Application and verification |
| --- | --- |
| Who does it | Candidate completes; sponsoring team member verifies |
| What happens | The candidate completes the application: career history, specialisms, the problems they solve stated in client language, proposed day rate (minimum £500), and two professional references. The sponsoring team member takes both references against the T07 reference question sheet by phone or call, and independently verifies the track record claims (companies, roles, outcomes). Verification is real: claims are checked, not accepted. |
| Document used | Application form, T07 Reference Question Sheet |
| Output | A completed application with two checked references and a verified track record |
| What triggers next | Verification complete |

| P5 | Founding team review |
| --- | --- |
| Who does it | Sponsoring team member presents; whole team decides |
| What happens | The sponsoring team member presents the candidate to the founding team: background, verification result, specialism fit, and any concerns. Any team member can raise an objection. A simple majority admits. The bar is the entry criteria, applied identically to everyone: eight-plus years at outcome-owning seniority, demonstrable delivery, verified references. Money never buys entry and no waiver lowers the bar. |
| Document used | Application pack from P4 |
| Output | An admit or decline decision, recorded |
| What triggers next | Decision made |

| P6 | Offer and membership agreement |
| --- | --- |
| Who does it | Sponsoring team member issues |
| What happens | The membership agreement (L02, once solicitor-approved) is issued with a covering letter. The letter states: their status (founding cohort if within the first 20, standard member otherwise), the fee position (£350 invoiced now, or waived with the contribution expectations stated plainly: two practitioner introductions or one client introduction within six months, profile live in 30 days), and the non-circumvention terms in summary. For founding cohort members the letter also states the renewal condition: year two free if the contribution expectation is met. |
| Document used | L02 Practitioner Membership Agreement, covering letter, T06 invoice (member 21+) |
| Output | A signed membership agreement and, where applicable, a paid fee |
| What triggers next | Agreement countersigned (and fee paid where applicable) |

| P7 | Profile build |
| --- | --- |
| Who does it | New member drafts; sponsoring team member reviews |
| What happens | The member builds their practitioner profile: specialism, the problems they solve in client language, day rate, engagement formats they accept, and career evidence. The sponsoring team member reviews it against one test: would a client reading this know exactly what problem this person ends? Profile goes live within 30 days of admission. A member with no profile adds no depth. |
| Document used | Profile template (website) |
| Output | A live, published practitioner profile |
| What triggers next | Profile published |

| P8 | Network onboarding |
| --- | --- |
| Who does it | Sponsoring team member |
| What happens | The member is introduced to the community, given access to the template library (T01 to T07), walked through the introduction registration process (T05) and the override economics, and reminded of the CMA rule: no discussion of day rates between members, ever, in any network channel. Rates are published individually on profiles; they are never discussed collectively. |
| Document used | Template library access, CMA compliance note |
| Output | A member who knows how everything works |
| What triggers next | Onboarding complete |

| P9 | 30-day check-in |
| --- | --- |
| Who does it | Sponsoring team member |
| What happens | A short call at 30 days: is the profile live, have they registered any introductions, are briefs reaching them, any friction anywhere. For founding cohort members, contribution progress is noted. This is also where most first introductions surface: ask directly who they know. |
| Document used | None (notes filed) |
| Output | An active member and, usually, the first introductions |
| What triggers next | Member enters normal network rhythm |

Section 2 · Journey C: The Client

From first contact to a registered, matchable brief. Target elapsed time: 5 to 15 days. Clients arrive by three routes: a referral partner introduction, a direct approach from the team, or inbound from the website. The route changes step C1 only; everything after is identical.

| C1 | First contact and registration of source |
| --- | --- |
| Who does it | Receiving team member |
| What happens | The client makes contact or is introduced. First action, before any substantive conversation: establish and record the source. If a referral partner or network member made the introduction, confirm a T05 introduction registration exists or is filed now. The override entitlement is timestamped by registration, and an unregistered introduction is an argument waiting to happen. Then the conversation: what is the problem, how long has it existed, what has been tried. |
| Document used | T05 Introduction Registration Form (if introduced) |
| Output | A recorded source and a first understanding of the problem |
| What triggers next | Client wants to proceed |

| C2 | The brief |
| --- | --- |
| Who does it | Client completes with team member support |
| What happens | The client completes the client brief: the problem (not a job description, not a person spec: the problem), the outcome they need, the timeline, the budget parameters, what they commit to providing, and who owns the engagement on their side. The team member helps sharpen it. A vague brief produces a bad match; this step earns the time it takes. The brief also captures which pillar the problem belongs to, which drives the match. |
| Document used | T02 Client Brief Form |
| Output | A completed, matchable brief |
| What triggers next | Brief accepted as complete by the receiving team member |

| C3 | Client engagement agreement and fee disclosure |
| --- | --- |
| Who does it | Receiving team member |
| What happens | The client engagement agreement (L03, once solicitor-approved) is issued alongside written confirmation of the fee structure they have already seen on the website: the practitioner's day rate plus 10% network fee, plus up to 5% in introduction overrides where applicable, capped at 15% total above day rate. No client ever discovers a fee on an invoice. The client 360 is explained: they will be rated too, their score persists, and a strong score means better practitioners choose them. |
| Document used | L03 Client Engagement Agreement, published fee schedule |
| Output | A signed client agreement and a client with zero fee surprises ahead |
| What triggers next | Agreement countersigned |

Section 3 · The Match

Where the two journeys meet: a registered brief matched to the practitioner who has already solved the problem. Target elapsed time: 5 working days from completed brief to introduction. This speed is a published commitment; protect it.

| M1 | Match search |
| --- | --- |
| Who does it | Receiving team member, with the whole team's input |
| What happens | The brief is matched against the network: specialism, problem history, pillar, availability, day rate against budget, and 360 score. The question is never 'who is free' but 'who has ended this exact problem before'. Where two or more practitioners fit, the client sees the strongest match first, not a beauty parade. If nobody in the network fits, say so to the client honestly and immediately: a forced match destroys more value than a declined brief. |
| Document used | T02 brief, practitioner profiles, 360 records |
| Output | A named practitioner match, or an honest no |
| What triggers next | Match identified |

| M2 | Practitioner approach |
| --- | --- |
| Who does it | Receiving team member |
| What happens | The matched practitioner receives the brief and, critically, the client's 360 score and history where one exists: payment record, scope clarity, how they treated the last practitioner. The practitioner decides with full information. They can decline for any reason, and a decline is respected without pressure. If they accept, availability and rate are confirmed against the brief. |
| Document used | T02 brief, client 360 record |
| Output | A practitioner who has accepted with eyes open |
| What triggers next | Practitioner accepts |

| M3 | The introduction meeting |
| --- | --- |
| Who does it | Team member convenes; practitioner and client meet |
| What happens | The practitioner and client meet before any commitment, always. The practitioner walks through how they have solved this problem before. The client walks through the situation in full. Chemistry matters and this meeting is where it is tested. No fee is payable by anyone for this meeting and no commitment exists on either side at its end. |
| Document used | None |
| Output | A mutual yes, or a no from either side |
| What triggers next | Both parties confirm they want to proceed |

| M4 | Override calculation lock |
| --- | --- |
| Who does it | Receiving team member |
| What happens | Before the SOW is drafted, the fee stack for this engagement is calculated and locked: day rate, 10% network fee, any peer introduction override (5%), any company introduction override (5%), capped at 15% total above day rate. Where both overrides apply, they split within the cap. The client sees the total daily cost in writing before the SOW. The practitioners entitled to overrides are named in the engagement record. |
| Document used | T05 registrations, fee schedule |
| Output | A locked, written fee stack for the engagement |
| What triggers next | Fee stack confirmed to client in writing |

Section 4 · The Statement of Work

The document that makes TWG different. Nothing starts without it, ever, for anyone, regardless of urgency. A client who will not sign a SOW is telling you something: listen.

| S1 | SOW drafting |
| --- | --- |
| Who does it | Practitioner drafts; team member supports |
| What happens | The practitioner drafts the SOW from the T01 template: the outcome, the deliverables, the KPIs and how they are measured, the milestones with dates, the engagement format (sprint, project, ongoing, advisory), days per week, day rate and total fee stack, payment terms (monthly, milestone, or agreed schedule), what the client commits to providing (access, data, decisions, a named internal owner), the named internal successor for knowledge transfer, and the exit condition: the specific state of the world on the day this engagement correctly ends. |
| Document used | T01 Statement of Work |
| Output | A draft SOW |
| What triggers next | Draft complete |

| S2 | SOW review |
| --- | --- |
| Who does it | Client reviews; team member mediates any negotiation |
| What happens | The client reviews the draft. Changes are negotiated openly and amended in the document, not agreed verbally. The team member's job in any negotiation is to protect the structure: a SOW without measurable KPIs, a named client-side owner, or an exit condition does not proceed, whatever the commercial pressure. |
| Document used | T01 (amended as needed) |
| Output | An agreed final SOW |
| What triggers next | Both parties confirm the final text |

| S3 | Signature |
| --- | --- |
| Who does it | Practitioner, client, and TWG sign |
| What happens | The SOW is signed by all parties before any work begins. Contracting structure note: pending the solicitor's answer, the intended model is that TWG contracts with the client and subcontracts to the practitioner, which is what makes the invoice flow in Section 6 work. The executed SOW is filed in the engagement record with the locked fee stack and the start date confirmed. |
| Document used | T01 executed |
| Output | A signed SOW, an engagement record, a start date |
| What triggers next | Start date arrives |

Section 5 · Delivery

Day one to final milestone. The practitioner delivers; the network's job is rhythm, visibility, and removing friction before it becomes conflict.

| D1 | Engagement start |
| --- | --- |
| Who does it | Practitioner and client-side owner |
| What happens | Work begins on the SOW start date. Week one includes a structured kick-off against the SOW: milestones restated, access and commitments confirmed delivered (the client's obligations start now too), the internal successor introduced and their development path agreed, and the review cadence booked into diaries for the whole engagement. |
| Document used | T01 (the reference document for everything) |
| Output | A running engagement with every review pre-booked |
| What triggers next | First review date |

| D2 | Milestone reviews |
| --- | --- |
| Who does it | Practitioner and client-side owner; team member joins where useful |
| What happens | Every two to four weeks per the SOW: progress against milestones, KPIs measured and recorded, blockers named (including client-side commitment failures, which are raised early and factually), and the knowledge transfer progress checked. Notes are filed to the engagement record every time. This running record is what makes the final 360 evidence-based rather than vibes-based, and it is what protects everyone if anything is later disputed. |
| Document used | Milestone review notes (filed to engagement record) |
| Output | A documented, current picture of the engagement |
| What triggers next | Each review completed; next one already booked |

| D3 | Scope change |
| --- | --- |
| Who does it | Either party proposes; both sign |
| What happens | Any change to scope, timeline, days, or deliverables requires a written SOW amendment signed by both parties before the changed work begins. Verbal scope changes do not exist in this model. The amendment updates the fee stack if days change, and the team member re-confirms the revised total to the client in writing. This single discipline kills the scope creep that poisons most fractional engagements. |
| Document used | SOW amendment (T01 addendum) |
| Output | An amended, signed SOW |
| What triggers next | Amendment executed; work continues |

| D4 | Mid-engagement pulse |
| --- | --- |
| Who does it | Team member |
| What happens | At the midpoint of any engagement over eight weeks, the team member takes a pulse from both sides separately: anything unsaid, any friction, any early signal of a problem. Ten minutes each. Most engagement failures announce themselves quietly at the midpoint and loudly at the end; this step hears the quiet version. |
| Document used | Pulse notes (filed) |
| Output | Early warning or clean bill |
| What triggers next | Any issue routes to Section 9; otherwise delivery continues |

Section 6 · Money

Who invoices whom, when everyone gets paid, and how the overrides flow. The intended model, pending solicitor confirmation of the contracting structure: money flows through TWG in both directions, which is what makes the escalation protection real.

| F1 | TWG invoices the client |
| --- | --- |
| Who does it | TWG (me, until an operations function exists) |
| What happens | Per the payment terms in the SOW (monthly in arrears as the default; milestone or other schedules where agreed), TWG invoices the client for: days delivered at the practitioner's day rate, plus the 10% network fee, plus any locked overrides, capped at 15% above day rate. The invoice matches the fee stack the client confirmed at M4 to the penny. Payment terms on the invoice: 14 days. |
| Document used | T06 Invoice |
| Output | An issued client invoice |
| What triggers next | Invoice issued; day counter starts |

| F2 | Practitioner pro forma |
| --- | --- |
| Who does it | TWG |
| What happens | Simultaneously, the practitioner receives a pro forma statement showing exactly what they are owed for the period: days delivered at their full rate, untouched. Where the practitioner has override earnings from other engagements (peer or company introductions), those appear on the same statement, itemised by engagement. The practitioner invoices TWG against the pro forma, or the pro forma serves as the self-billing record where that is agreed. |
| Document used | Pro forma statement, T06 |
| Output | A practitioner statement with zero ambiguity about what is owed |
| What triggers next | Client payment received |

| F3 | Client pays; practitioner paid |
| --- | --- |
| Who does it | Client pays TWG; TWG pays practitioner |
| What happens | The client pays TWG within 14 days. TWG pays the practitioner their full day-rate amount, and pays any override amounts to the entitled introducers, within 5 working days of cleared client funds. The network fee remains with TWG. Every payment is recorded to the engagement record. |
| Document used | Remittances, engagement record |
| Output | Everyone paid, everything recorded |
| What triggers next | Next invoicing period, or engagement close |

| F4 | Late payment: day 15 |
| --- | --- |
| Who does it | TWG, never the practitioner |
| What happens | The day a client invoice passes 14 days unpaid, escalation begins and it is the network that escalates, never the individual practitioner. Day 15: a formal reminder from TWG citing the SOW terms. Day 21: a direct call from a founding team member to the client-side owner. Day 28: written notice that work pauses at day 35 and statutory interest (8% plus base) applies per the client agreement. Day 35: work pauses until payment clears. The practitioner is kept informed at every step and never has to chase their own money. The client's payment conduct is recorded and feeds their 360. |
| Document used | Escalation letters (standard wording), engagement record |
| Output | Payment recovered, or a paused engagement and a documented record |
| What triggers next | Payment clears (work resumes) or dispute routes to Section 9 |

The override arithmetic, worked

| Scenario | Client pays / day | Practitioner gets | Introducer gets | TWG gets |
| --- | --- | --- | --- | --- |
| No introductions. £1,000 rate | £1,100 | £1,000 | None | £100 |
| Peer introduction. £1,000 rate | £1,150 | £1,000 | £50 / day, life of engagement | £100 |
| Company introduction. £1,000 rate | £1,150 | £1,000 | £50 / day, every contract, lifetime | £100 |
| Both apply. £1,000 rate | £1,150 (15% cap) | £1,000 | £50 split per cap rules | £100 |

ℹ  The £350 annual membership fee is entirely separate from engagement money. It is invoiced at joining and renewal (P6), never appears on engagement invoices, and is never deducted from anything.

Section 7 · The Close

The engagement ends the way it started: on terms everyone agreed in writing. The close is triggered by the final milestone or the exit condition in the SOW being met.

| E1 | Exit condition check |
| --- | --- |
| Who does it | Practitioner and client-side owner, against the SOW |
| What happens | The final milestone review checks the exit condition as written in the SOW: is the specific state of the world it describes now true? Deliverables are checked off, KPIs are measured a final time against the record built through D2, and anything genuinely outstanding is either completed or explicitly agreed as out of scope with reasons recorded. |
| Document used | T01 (exit condition), milestone record |
| Output | A confirmed, evidenced completion |
| What triggers next | Both parties confirm the exit condition is met |

| E2 | Knowledge transfer confirmation |
| --- | --- |
| Who does it | Practitioner, successor, and client-side owner |
| What happens | The named successor demonstrates they are running what was built: not a handover document, a working demonstration. The practitioner's mentoring obligation is discharged when the client-side owner confirms in writing that the internal team operates the capability independently. This confirmation is the difference between TWG and every consultancy the client has used before; treat it with that weight. |
| Document used | Knowledge transfer confirmation (filed to engagement record) |
| Output | A client team running it themselves, confirmed in writing |
| What triggers next | Confirmation filed |

| E3 | Final invoice and settlement |
| --- | --- |
| Who does it | TWG |
| What happens | The final invoice issues per Section 6, including any final-period overrides. All payments settle. The engagement record is financially closed: total days, total paid, overrides distributed, no balance outstanding on any side. |
| Document used | T06, engagement record |
| Output | A financially closed engagement |
| What triggers next | All payments cleared |

| E4 | The bilateral 360 |
| --- | --- |
| Who does it | Both parties, within 10 days of close |
| What happens | Both sides complete their evaluation. The practitioner is rated by the client on delivery against the SOW, communication, and the knowledge transfer (T03). The client is rated by the practitioner on outcome clarity, responsiveness, treatment of the practitioner, and payment conduct (T04), with the payment record from Section 6 feeding in automatically. Both scores are threshold-checked: scores below threshold trigger a founding team review of that party's continued standing in the network, per the governance framework. Both scores persist and compound. |
| Document used | T03 Practitioner 360, T04 Client 360 |
| Output | Two recorded scores, both permanent |
| What triggers next | Both evaluations filed |

| E5 | Case study decision |
| --- | --- |
| Who does it | Team member with the client |
| What happens | With the engagement closed and scored, the client is asked whether the engagement can be documented as a case study, named or anonymised. A yes triggers the case study process; a no is filed without pressure. Nothing is ever published without written permission and nothing is ever invented. The first twenty of these are worth more than the entire marketing budget. |
| Document used | Case study permission (written) |
| Output | A documented case study, or a respected no |
| What triggers next | Engagement fully closed |

Section 8 · After the Engagement

- Scores compound. The practitioner's 360 updates their profile and strengthens their next match. The client's 360 is visible to every practitioner they approach in future: a strong score means better practitioners say yes faster.

- Follow-on work is new work. Any further engagement with the same client, by the same or any other practitioner, starts at C2 with a new brief and a new SOW. Company introduction overrides continue automatically on every follow-on: the original introducer earns on all of it, forever.

- Non-circumvention holds for 24 months. Neither client nor practitioner engages the other outside the network within 24 months of the last engagement day. The pre-agreed liquidated damages formula (days worked outside × day rate × 10%, plus 20% administration premium) applies without needing to prove loss.

- Renewals run on the anniversary. Practitioner membership renews at £350 (P6 letter states the founding cohort conditions). A member with no activity, no profile, and no engagement in the year triggers a check-in before renewal, not an automatic invoice.

- Alumni matter. A practitioner who leaves the network in good standing leaves with their 360 record acknowledged, the door open, and the non-circumvention terms intact.

Section 9 · Escalations and Exceptions

The paths for when things go wrong. Every one starts the same way: early, factual, and through the network rather than between the individuals.

Late payment

Fully specified at F4. The one rule worth repeating: the practitioner never chases. The network does.

Engagement in trouble

Raised by either party, or surfaced at the D4 pulse. A founding team member convenes both sides within 5 working days. The SOW is the reference: what does it say, what has each side delivered against its commitments, what does the milestone record show. Most trouble resolves here because the paperwork removes the ambiguity that fuels most disputes. Outcomes: a course correction recorded in the engagement record, a signed SOW amendment, or a managed early exit.

Managed early exit

Where an engagement should end early (the problem dissolves, the client's situation changes, the relationship fails), the exit is managed, not abandoned: days delivered are invoiced and paid per Section 6, knowledge transfer happens to whatever state the work has reached, both 360s complete (covering the engagement as it actually ran), and the reasons are recorded factually in the engagement record. An early exit handled well protects everyone's record; a walkout destroys three reputations including ours.

Circumvention

Where a client and practitioner engage outside the network within the 24-month window, the liquidated damages clause applies: the formula is pre-agreed in both the membership and client agreements, requiring no proof of loss. First response is always a factual letter citing the clause and inviting regularisation (the engagement comes back inside the network); enforcement is the last resort but a real one. Detection sources: the practitioner community, referral partners, and the visibility that comes from a small, connected market.

360 threshold breach

A score below threshold on either side triggers a founding team review within 14 days: the record is examined, the party is heard, and the outcomes range from a noted concern, to conditions on future engagements, to removal from the network. The threshold consequences apply identically to clients and practitioners: that symmetry is the entire point of the bilateral system.

Dispute the process cannot resolve

Anything the above does not resolve follows the dispute resolution provisions of the L-series agreements (mediation before litigation, English law, per the solicitor-approved final terms). The engagement record built through D2, F4, and E1 to E4 is the evidence base; this is why every step files its paperwork.

Section 10 · The Complete Document Map

| Document | Used at | Purpose | Owner |
| --- | --- | --- | --- |
| TWG_Mutual_NDA_v1_Clean | P2, and any client pre-brief confidentiality | Confidentiality before anything is shared. The only NDA version that exists. | Sponsoring team member |
| Foundation Document v1.2 | P3 | The complete model for the incoming practitioner. | TWG |
| Founding Practitioner Brief v2 | P3 | Economics and founding status. | TWG |
| Membership Value doc | P3 | The £350 value case. | TWG |
| T07 Reference Question Sheet | P4 | Structured reference checks. Both references, every candidate. | Sponsoring team member |
| L02 Practitioner Membership Agreement | P6 | The membership contract: fee, non-circumvention, CMA rule, conduct. DRAFT until solicitor sign-off. | TWG |
| T06 Invoice | P6, F1, F2, E3 | Membership fee invoicing and all engagement invoicing. | TWG |
| T05 Introduction Registration | C1, M4, and any member introduction at any time | Timestamps every override entitlement. Registered before contact, always. | Introducer |
| T02 Client Brief Form | C2, and every follow-on engagement | The problem, captured matchably. | Client + team member |
| L03 Client Engagement Agreement | C3 | The client contract: fees, 360, non-circumvention, escalation terms. DRAFT until sign-off. | TWG |
| T01 Statement of Work | S1 to S3, D1, D3, E1 | The engagement's constitution: outcomes, KPIs, milestones, commitments, exit condition. Amendments in writing only. | Practitioner drafts |
| Milestone review notes | D2, D4 | The running evidence base of every engagement. | Practitioner |
| T03 Practitioner 360 | E4 | Client rates practitioner. Permanent. | Client |
| T04 Client 360 | E4 | Practitioner rates client. Permanent. Payment conduct feeds in from F4. | Practitioner |
| Knowledge transfer confirmation | E2 | Written client confirmation the internal team runs it. The proof of the differentiator. | Client-side owner |
| Case study permission | E5 | Written permission before anything is documented publicly. | Team member |
| L04 Terms and Conditions | Website / platform | Public-facing terms. DRAFT until sign-off. | TWG |

The Whole Model on One Page

P1 to P9: a practitioner is met, protected by NDA, informed, verified, admitted by the team, signed, published, onboarded, and activated. C1 to C3: a client's source is registered, their problem is captured as a brief, and they sign with every fee already known. M1 to M4: the match is made on problem history, the practitioner accepts with the client's record in view, both meet before committing, and the money is locked in writing. S1 to S3: the outcome, the measures, the commitments, and the exit are signed before day one. D1 to D4: delivery runs on a booked rhythm, everything is filed, and scope changes only in writing. F1 to F4: TWG invoices, the practitioner is paid in full within days of cleared funds, overrides flow to their owners, and the network, never the practitioner, chases anything late. E1 to E5: the exit condition is evidenced, the client's own team demonstrates the capability, the money settles, both sides are scored permanently, and the case study is asked for, never assumed. And after: scores compound, follow-ons are new SOWs, the introducer earns forever, and the 24-month non-circumvention holds.

If a step is not in this document, it is not in the model. If it is in this document, it is done the same way every time, by everyone, for everyone.

TWG Network   ·   The Engagement Model v1.0   ·   Founding team   ·   Confidential   ·   July 2026   ·   Reissues as v1.1 on solicitor sign-off